## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Sebastian | 11200 | 9425 | 1775 | 4400 | 5900 | -1500 | 1000 | 325 | 675 | 1800 | 1500 | 300 | 4000 | 1700 | 2300
Zoe | 10900 | 14000 | -3100 | 4300 | 3800 | 500 | 1000 | 200 | 800 | 1600 | 1400 | 200 | 4000 | 8600 | -4600
Aiden | 11100 | 5950 | 5150 | 4800 | 2200 | 2600 | 1000 | 525 | 475 | 1300 | 825 | 475 | 4000 | 2400 | 1600
Andrew | 12000 | 14350 | -2350 | 4500 | 3550 | 950 | 1000 | 725 | 275 | 2500 | 2675 | -175 | 4000 | 7400 | -3400
Dylan | 8400 | 6900 | 1500 | 1700 | 2500 | -800 | 1000 | 450 | 550 | 1700 | 1200 | 500 | 4000 | 2750 | 1250
Joe | 7200 | 3025 | 4175 | 1100 | 500 | 600 | 1000 | 275 | 725 | 1100 | 450 | 650 | 4000 | 1800 | 2200
Total | 60800 | 53650 | 7150 | 20800 | 18450 | 2350 | 6000 | 2500 | 3500 | 10000 | 8050 | 1950 | 24000 | 24650 | -650

## Gantt
| predicted time(hrs) | time spent(hrs) | Status | key | complete | in progress | planned
Sebastian |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Design Dialogue Tree/Chat System | 4 | 4 | complete | key 1: complete; complete 2: complete; in progress 3: complete; planned 4: complete
Design NPC Class | 3 | 3 | complete | planned 5: complete; planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
Design NPC Child Class | 3 | 3 | in progress | planned 11: in progress; planned 12: in progress; planned 13: in progress
Design Characters For NPC Objects | 5 | 8 | in progress | planned 20: in progress; planned 21: in progress; planned 22: in progress; planned 23: in progress; planned 24: in progress; planned 25: in progress; planned 26: in progress; planned 27: in progress
Class Documentation | 6 | 1 | complete | planned 14: complete
Programming | 15 | 32 | in progress | planned 5: in progress; planned 6: in progress; planned 7: in progress; planned 8: in progress; planned 9: in progress; planned 10: in progress; planned 25: in progress; planned 26: in progress; planned 27: in progress; planned 28: in progress; planned 29: in progress; planned 30: in progress; planned 31: in progress; planned 32: in progress; planned 33: in progress; planned 34: in progress; planned 35: in progress; planned 36: in progress; planned 37: in progress; planned 38: in progress; planned 39: in progress; planned 40: in progress; planned 41: in progress; planned 42: in progress; planned 43: in progress; planned 44: in progress; planned 45: in progress; planned 46: in progress; planned 47: in progress; planned 48: in progress; planned 49: in progress
Testing | 3 | 3 | complete | planned 15: in progress; planned 16: in progress; planned 17: in progress; planned 18: in progress; planned 19: in progress; planned 29: complete; planned 30: complete; planned 31: complete
Sound Design | 5 | 5 | complete | planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete
totals | 44 | 59
Zoe
Graphics (Prototype) | 5 | 7 | complete | key 1: complete; complete 2: complete; in progress 3: complete; planned 4: complete; planned 5: complete
Graphics Complete | 15 | 9 | in progress | planned 6: in progress; planned 7: in progress; planned 8: in progress; planned 9: in progress; planned 10: in progress; planned 11: in progress; planned 12: in progress; planned 13: in progress; planned 14: in progress; planned 15: in progress; planned 16: in progress; planned 17: in progress; planned 18: in progress; planned 19: in progress; planned 20: in progress
Map Design | 8 | 2 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete; planned 11: complete; planned 12: complete; planned 13: complete
Lighting | 5 | 0 | planned | planned 14: planned; planned 15: planned; planned 16: planned; planned 17: planned; planned 18: planned
Map Collision/Physics | 5 | 0 | complete | planned 14: complete; planned 15: complete; planned 16: complete; planned 17: complete; planned 18: complete
Destinations (Quests) | 1 | 14 | complete | planned 14: complete
Testing | 3 | 6 | planned | planned 19: planned; planned 20: planned; planned 21: planned
Installation | 1 | 0 | planned | planned 22: planned
totals | 43 | 38
Aiden
Acceleration/Deceleration | 4 | 3 | complete | key 1: complete; complete 2: complete; in progress 3: complete
Turning/Steering | 4 | 2 | complete | planned 4: complete; planned 5: complete; planned 6: complete; planned 7: complete
Braking | 3 | 2 | complete | planned 8: complete; planned 9: complete; planned 10: complete
Brake Lights | 5 | 0 | planned | planned 11: planned; planned 12: planned; planned 13: planned; planned 14: planned; planned 15: planned
Headlight Lights | 2 | 0 | planned | planned 16: planned; planned 17: planned
Smoke Particle Effects | 3 | 0 | complete | planned 4: complete; planned 5: complete; planned 6: complete
Health/Damage | 8 | 0 | planned | planned 4: planned; planned 5: planned; planned 6: planned; planned 7: planned; planned 8: planned; planned 9: planned; planned 10: planned; planned 11: planned
Friction/Traction | 6 | 0 | complete | planned 8: complete; planned 9: complete; planned 10: complete; planned 11: complete; planned 12: complete; planned 13: complete
Animation/Visual Status | 5 | 9 | complete | planned 8: complete; planned 9: complete; planned 10: complete; planned 11: complete; planned 12: complete
Testing/Installation | 8 | 6 | complete | planned 18: complete; planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete
Totals | 48 | 22
Andrew
Implement Game Timer | 3 | 5.25 | complete | key 1: complete; complete 2: complete; in progress 3: complete
Request Pizza Function | 4 | 5.25 | complete | planned 4: complete; planned 5: complete; planned 6: complete; planned 7: complete
Generate And Place Pizza in Environment | 5 | 4 | complete | planned 8: complete; planned 9: complete; planned 10: complete; planned 11: complete; planned 12: complete
Pick Up Pizza | 3 | 4 | complete | planned 13: complete; planned 14: complete; planned 15: complete
Navigate Environment With Pizza | 5 | 0.75 | complete | planned 16: complete; planned 17: complete; planned 18: complete; planned 19: complete; planned 20: complete
Check If Character Is In Proximity Of Delivery Environment | 4 | 0.5 | complete | planned 4: complete; planned 5: complete; planned 6: complete; planned 7: complete
Drop Off Pizza At Destination | 5 | 0.5 | complete | planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete; planned 25: complete
Calculate And Reward Character Points | 4 | 3.75 | complete | planned 26: complete; planned 27: complete; planned 28: complete; planned 29: complete
Testing Of Individual Responsibilities | 6 | 8.5 | complete | planned 30: complete; planned 31: complete; planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete
Integration Of Individual Responsibilities With Team's Work | 6 | 3 | complete | planned 36: complete; planned 37: complete; planned 38: complete; planned 39: complete; planned 40: complete; planned 41: complete
totals | 45 | 35.5
Dylan
Develop Menus | 4 | 4 | complete | key 1: complete; complete 2: complete; in progress 3: complete; planned 4: complete
Polish Menus | 1 | 1 | complete | planned 5: complete
Code Monster | 6 | 10 | in progress | planned 6: in progress; planned 7: in progress; planned 8: in progress; planned 9: in progress; planned 10: in progress; planned 11: in progress
Test Monster | 3 | 10 | in progress | planned 12: in progress; planned 13: in progress; planned 14: in progress
Record Demos | 3 | 0 | planned | planned 15: planned; planned 16: planned; planned 17: planned
totals | 17 | 25
Joe (Actually More Zoë)
Upgrades Design | 1 | 0 | planned | key 1: planned
Program Game Scene Handling | 2 | 0 | planned | key 1: planned; complete 2: planned
Program Abstract Upgrade Classes Implementation | 2 | 0 | planned | complete 2: planned; in progress 3: planned
Program Player Status Modification | 2 | 0 | planned | planned 4: planned; planned 5: planned
Program HUD | 1 | 5 | complete | planned 6: complete
Testing | 2 | 0 | planned | planned 7: planned; planned 8: planned
Finalization/Ship | 1 | 0 | planned | planned 9: planned
totals | 11 | 5
group totals (hrs) | 180 | 154.5
group totals ($) | 18000 | 15450

## Meetings
| Date | 2024-01-23 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-03-11 | 2024-03-22 | 2024-03-25 | 2024-03-27 | 2024-04-05 | 2024-04-10 | */*/* | */*/* | */*/* | */*/* | */*/* | */*/* | */*/* | */*/* | */*/* | */*/* | */*/* | */*/* | */*/*
| Purpose | First Meeting | Meeting with Dr. BC | Meeting with Dr. BC (Cont.) | Meeting with teammates | Meeting with Dr. BC | Meeting with Dr. BC | Meeting with Dr. BC and TL 4s | Meeting between Dylan and Andrew | Meeting with Dr. BC | Expectation Meeeting | Implementing attack score damage | * | * | * | * | * | * | * | * | * | * | * | * | *
| Hours | 1 | 0.5 | 1.25 | 0.5 | 0.75 | 0.75 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sebastian | 3.25 | ü |  | ü | [6 empty] | ü |  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Zoe | 2 | ü | [8 empty] | ü |  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Aiden | 5.25 | ü |  | ü | [5 empty] | ü | ü |  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Andrew | 7.25 | ü | ü | ü |  | ü | ü | ü | ü |  |  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Dylan | 4.5 | ü |  |  | ü |  |  |  | ü |  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Joe | 2.75 | ü |  | ü | ü | [7 empty] | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Total | 25 | 6 | 0.5 | 5 | 1 | 0.75 | 0.75 | 1 | 2 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Sebastian | RFP | 3 | 2.5 | bar: 1 to 3
| Champion | 6 | 5 | bar: 4 to 9
| Presentation Preperation | 8 | 7 | bar: 10 to 17
| Presenting | 1 | 0.5 | bar: 18
| Subtotal | 18 | 15
Zoe | RFP | 3 | 2.5 | bar: 1 to 3
| Champion | 4 | 4 | bar: 4 to 7
| Presentation Preperation | 8 | 7 | bar: 8 to 15
| Presenting | 1 | 0.5 | bar: 16
| Subtotal | 16 | 14
Aiden | RFP | 3 | 2.25 | bar: 1 to 3
| Champion | 4 | 3 | bar: 4 to 7
| Presentation Preperation | 5 | 2.5 | bar: 8 to 12
| Presenting | 1 | 0.5 | bar: 13
| Subtotal | 13 | 8.25
Andrew | RFP | 4 | 2.5 | bar: 1 to 4
| Champion | 12 | 15.75 | bar: 5 to 16
| Presentation Preperation | 8 | 8 | bar: 17 to 24
| Presenting | 1 | 0.5 | bar: 25
| Subtotal | 25 | 26.75
Dylan | RFP | 3 | 1.5 | bar: 1 to 3
| Champion | 5 | 4 | bar: 4 to 8
| Presentation Preperation | 5 | 6 | bar: 9 to 13
| Presenting | 4 | 0.5 | bar: 14 to 17
| Subtotal | 17 | 12
Joe | RFP | 3 | 2.5 | bar: 1 to 3
| Champion | 2 | 2 | bar: 4 to 5
| Presentation Preperation | 5 | 0 | bar: 6 to 10
| Presenting | 1 | 0 | bar: 11
| Subtotal | 11 | 4.5
| Total | 100 | 80.5
red is dependent on others

## Overhead
| Sebastian | Zoe | Aiden | Andrew | Dylan | Joe
Designing Graphics | 0 | 11 | 0 | 0 | 3.5 | 0
Platformer Coding | 0 | 42 | 0 | 20 | 6 | 0
Team Lead Presentation Prep | 0 | 5 | 1 | 19 | 0 | 0
Team Lead Help | 0 | 10 | 5 | 0 | 0 | 0
Software Specialist Presentation Prep | 0 | 0 | 0 | 0 | 0 | 0
Oral Exam Prep | 0 | 0 | 0 | 0 | 0 | 0
Test Plan | 0 | 0 | 0 | 7.5 | 0 | 0
Prefab Documentation | 0 | 0 | 0 | 2 | 0 | 0
Dynamic Binding | 0 | 0 | 0 | 1.75 | 0 | 0
Copyright Research | 0 | 0 | 0 | 3.75 | 0 | 0
Pattern Research | 0 | 0 | 0 | 2 | 0 | 0
Post Mortum Presentation Prep | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 68 | 6 | 56 | 9.5 | 0
Training | Sebastian | Zoe | Aiden | Andrew | Dylan | Joe
TL 1 Git Training | 2 | 2 | 2 | 2 | 2 | 2
TL 2 Unity Training | 6 | 6 | 6 | 6 | 6 | 6
TL 3 Quality Assurance Training | 4 | 4 | 4 | 4 | 4 | 4
TL 4 Software Management Training | 1 | 1 | 1 | 1 | 1 | 1
TL 5 AI Training | 1 | 1 | 1 | 1 | 1 | 1
TL 6 Version Control Training | 1 | 1 | 1 | 1 | 1 | 1
Other Training | 2 | 3 | 3 | 3 | 3 | 3
Total | 17 | 18 | 18 | 18 | 18 | 18

## Team Mate Delverables
TL 1 Deliverables |  |  | TL 2 Deliverables |  |  | TL 3 Deliverables |  | TL 4 Deliverables |  | TL 5 Deliverables | TL 6 Deliverables
Date Due: 2/13/2024 |  |  | Date Due: 2/29/2024 |  |  | Date Due: 3/5/2024 |  | Date Due: 3/26/2024 & 3/28/2024 |  | Date Due: 4/5/2024 | Date Due: 4/9/2024 & 4/11/2024
By Tuesday 2/13/2024: Initial Readme File in GIT |  |  | By Thursday 2/29/2024: Initial function in GIT that the MVP can call |  |  | By Tuesday 3/5/2024: Submit to GIT: 2 Boundary Tests 1 Stress Test |  | By Tuesday 3/26/2024: |  | By Wednesday | By Monday 4/9/2024:
[8 empty] | 1. Fully update your sections of the Gantt chart |  | 4/5/2024 at 6pm:
1: Update the gantt for what you have worked on.
[8 empty] | By Thursday 3/28/2024: |  | 2: Send me an update on what you have been working on this week.
1. Look over the coding standards in the GIT
2. Try to update your code to comply with the coding standards (to the best of your ability, BC is not expecting it to be perfect). Message me when you're done and I'll check you off.
Location: |  |  | Location: |  |  | Location: |  | Location: |  | Location: | Location:
Get deliverables to TL by 6pm on Date Due
Deliverable Tracker
| Sebastian | Zoe | Aiden | Andrew | Dylan | Joe | Key:
TL 1 | ü | ü | ü | ü | ü | ü | Complete: |  | ü
TL 2 | ü | ü | ü | ü | ü |  | Incomplete: |  | -
TL 3 | ü | ü | ü | ü | ü
TL 4 | ü | ü | ü | ü | ü
TL 5 | ü | ü | ü | ü | ü
TL 6 | ü | ü | ü | ü | ü | ü